## EVM - Graph
EVA Graphs for <Project X>
S
| Condition | Project Status
| Earned Value above Actual Costs (Green line above Red Line) | Under Budget
| Earned Value below Actual Costs (Green line below Red Line) | Over Budget
| Earned Value above Planned Value (Green line above Blue Line) | Ahead of Schedule
| Earned Value below Planned Value (Green line below Blue Line) | Behind Schedule
| Condition | Project Status
| CPI greater than one | Under Budget
| CPI less than one | Over Budget
| SPI greater than one | Ahead of Schedule
| SPI less than one | Behind Schedule

## EVM
Combined - Project Status
Project = <Project X>
Last Updated: | <mm/dd/yyyy>
Week Starting | Planned Value | Actual Cost (Hours) | ETC | % Complete | Earned Value | Cost Variance | Schedule Variance | Cost Performance Index (CPI) | Schedule Performance Index (SPI) | EAC | Target
| PV | AC |  |  |  | EV - AC = CV | EV - PV = SV | (EV/AC) | (EV/PV)
2012-01-01 | 200 | 431 | 5500 | 11.29% | 700 | 269 | 500 | 1.6241 | 3.5 | 5931 | 1
2012-01-08 | 400 | 608 | 5400 | 12.9% | 800 | 192 | 400 | 1.3158 | 2 | 6008 | 1
2012-01-15 | 700 | 729 | 5300 | 14.52% | 900 | 171 | 200 | 1.2346 | 1.2857 | 6029 | 1
2012-01-22 | 800 | 861 | 5000 | 19.35% | 1200 | 339 | 400 | 1.3937 | 1.5 | 5861 | 1
2012-01-29 | 1000 | 968 | 4900 | 20.97% | 1300 | 332 | 300 | 1.343 | 1.3 | 5868 | 1
2012-02-05 | 1250 | 1075 | 4500 | 27.42% | 1700 | 625 | 450 | 1.5814 | 1.36 | 5575 | 1
2012-02-12 | 1600 | 1240 | 4200 | 32.26% | 2000 | 760 | 400 | 1.6129 | 1.25 | 5440 | 1
2012-02-19 | 2000 | 1412 | 4100 | 33.87% | 2100 | 688 | 100 | 1.4873 | 1.05 | 5512 | 1
2012-02-26 | 2400 | 1517 | 4000 | 35.48% | 2200 | 683 | -200 | 1.4502 | 0.91667 | 5517 | 1
2012-03-04 | 2830 | 1636 | 4000 | 35.48% | 2200 | 564 | -630 | 1.3447 | 0.77739 | 5636 | 1
2012-03-11 | 3200 | 1785 | 3900 | 37.1% | 2300 | 515 | -900 | 1.2885 | 0.71875 | 5685 | 1
2012-03-18 | 3650 | 1878 | 3850 | 37.9% | 2350 | 472 | -1300 | 1.2513 | 0.64384 | 5728 | 1
2012-03-25 | 4100 | 1949 | 3800 | 38.71% | 2400 | 451 | -1700 | 1.2314 | 0.58537 | 5749 | 1
2012-04-01 | 4500 | [9 empty] | 1
2012-04-08 | 4850 | [9 empty] | 1
2012-04-15 | 5100 | [9 empty] | 1
2012-04-22 | 5400 | [9 empty] | 1
2012-04-29 | 5480 | [9 empty] | 1
2012-05-06 | 5560 | [9 empty] | 1
2012-05-13 | 5640 | [9 empty] | 1
2012-05-20 | 5720 | [9 empty] | 1
2012-05-27 | 5800 | [9 empty] | 1
2012-06-03 | 5880 | [9 empty] | 1
2012-06-10 | 5960 | [9 empty] | 1
2012-06-17 | 6040 | [9 empty] | 1
2012-06-24 | 6120 | [9 empty] | 1
2012-07-01 | 6200 | [9 empty] | 1
1
Total Budget | 6200 | [9 empty] | 1
Notes:
1. Planned Value (PV) is the number of hours of work that will be completed according to the plan through the end of the specified week. It is determined during planning and populated for every week at the start of the project. This will account for holidays, vacations, admin time, etc.
2. Actual Cost (AC) is the number of hours of work that has been spent through the end of the specified week.
3. ETC is provided at the end of each week.
4. The other columns are calculated values.
Formulas:
Week Starting = [Week Starting, row above]+7