## Data-Mar11
Project A Risk Register (Partial) - Mar 2011 |  |  |  |  | 43
Id | Risk Description | Probability |  | Impact (Delays in # of days) | EMV (C*E)
|  | (%) | L/M/H
1 | Delays in completing the Data Model | 40% | M | 15 | 6
2 | Impact is very large because of new data model | 10% | L | 10 | 1
3 | Sharing of tables gets minimized to keep the impact low | 30% | M | 10 | 3
4 | Data migration is not final until end of Nov 11 | 50% | M | 15 | 7.5
5 | Conversion of Group1 programs gets delayed | 50% | M | 15 | 7.5
6 | Batch Cycle becomes longer | 40% | M | 5 | 2
7 | Project X - taking the resources away from this project | 80% | H | 15 | 12
8 | Other new product - Taking resources away | 80% | M | 5 | 4
43
Note on D3: ANPAC: L - <30% M - >30%, <60% H - >60%

## Data-May11
Project A Risk Register (Partial) - May 2011
Id | Risk Description | Probability |  | Impact (Delays in # of days) | EMV (C*E)
|  | (%) | L/M/H
1 | Delays in completing the Data Model | 30% | L | 10 | 3
2 | Impact is very large because of new data model | 10% | L | 10 | 1
3 | Sharing of tables gets minimized to keep the impact low | 20% | L | 5 | 1
4 | Data migration is not final until end of Nov 11 | 50% | M | 15 | 7.5
5 | Conversion of G1 programs gets delayed | 60% | M | 15 | 9
6 | Batch Cycle becomes longer | 40% | M | 5 | 2
7 | Project X - taking the resources away from this project | 80% | H | 15 | 12
8 | Project Y Implementation of Base Layer gets delayed | 10% | L | 10 | 1
9 | Datawarehouse can't handle new data by end of Dec 11 | 50% | M | 20 | 10
10 | Other new product - Taking resources away | 80% | M | 5 | 4
46.5
Note on D4: ANPAC: L - <30% M - >30%, <60% H - >60%

## Data-Jul11
Project A Risk Register (Partial) - Jul 2011
Id | Risk Description | Probability |  | Impact (Delays in # of days) | EMV (C*E)
|  | (%) | L/M/H
1 | Delays in completing the Data Model | 0% | L | 10 | 0
2 | Impact is very large because of new data model | 0% | L | 10 | 0
3 | Sharing of tables gets minimized to keep the impact low | 0% | L | 5 | 0
4 | Data migration is not final until end of Nov 11 | 30% | L | 10 | 3
5 | Conversion of G1 programs gets delayed | 50% | M | 10 | 5
6 | Batch Cycle becomes longer | 40% | M | 5 | 2
7 | Project X - taking the resources away from this project | 80% | H | 15 | 12
8 | Project Y Implementation of Base Layer gets delayed | 10% | L | 10 | 1
9 | Datawarehouse can't handle new data by end of Dec 11 | 50% | M | 20 | 10
10 | Other new product - Taking resources away | 80% | M | 5 | 4
33
Note on D4: ANPAC: L - <30% M - >30%, <60% H - >60%

## Data-Aug11
Project A Risk Register (Partial) - Aug 2011
Id | Risk Description | Probability |  | Impact (Delays in # of days) | EMV (C*E)
|  | (%) | L/M/H
1 | Delays in completing the Data Model | 0% |  | 0 | 0
2 | Impact is very large because of new data model | 0% |  | 0 | 0
3 | Sharing of tables gets minimized to keep the impact low | 0% |  | 0 | 0
4 | Data migration is not final until end of Nov 11 | 5% | L | 2 | 0.1
5 | Conversion of G1 programs gets delayed | 15% | L | 10 | 1.5
6 | Batch Cycle becomes longer | 30% | L | 15 | 4.5
7 | Project X - taking the resources away from this project | 80% | H | 10 | 8
8 | Project Y Implementation of Base Layer gets delayed | 10% | L | 10 | 1
9 | Datawarehouse can't handle new data by end of Dec 11 | 50% | M | 20 | 10
10 | Other new product - Taking resources away | 30% | L | 10 | 3
28.1
Note on D4: ANPAC: L - <30% M - >30%, <60% H - >60%

## Data-Sep11
Project A Risk Register (Partial) - Sep 2011
Id | Risk Description | Probability |  | Impact (Delays in # of days) | EMV (C*E)
|  | (%) | L/M/H
1 | Delays in completing the Data Model | 0% |  | 0 | 0
2 | Impact is very large because of new data model | 0% |  | 0 | 0
3 | Sharing of tables gets minimized to keep the impact low | 0% |  | 0 | 0
4 | Data migration is not final until end of Nov 11 | 5% | L | 2 | 0.1
5 | Conversion of G1 programs gets delayed | 15% | L | 10 | 1.5
6 | Batch Cycle becomes longer | 30% | L | 15 | 4.5
7 | Project X - taking the resources away from this project | 50% | H | 10 | 5
8 | Project Y Implementation of Base Layer gets delayed | 10% | L | 10 | 1
9 | Datawarehouse can't handle new data by end of Dec 11 | 50% | M | 20 | 10
10 | Other new product - Taking resources away | 30% | L | 10 | 3
25.1
Note on D4: ANPAC: L - <30% M - >30%, <60% H - >60%

## Data-Oct11
Project A Risk Register (Partial) - Oct 2011
Id | Risk Description | Probability |  | Impact (Delays in # of days) | EMV (C*E)
|  | (%) | L/M/H
1 | Delays in completing the Data Model | 0% |  | 0 | 0
2 | Impact is very large because of new data model | 0% |  | 0 | 0
3 | Sharing of tables gets minimized to keep the impact low | 0% |  | 0 | 0
4 | Data migration is not final until end of Nov 11 | 5% | L | 2 | 0.1
5 | Conversion of G1 programs gets delayed | 5% | L | 10 | 0.5
6 | Batch Cycle becomes longer | 30% | L | 15 | 4.5
7 | Project X - taking the resources away from this project | 50% | H | 10 | 5
8 | Project Y Implementation of Base Layer gets delayed | 10% | L | 10 | 1
9 | Datawarehouse can't handle new data by end of Dec 11 | 50% | M | 20 | 10
10 | Other new product - Taking resources away | 30% | L | 10 | 3
24.1
Note on D4: ANPAC: L - <30% M - >30%, <60% H - >60%

## Data-Nov11
Project A Risk Register (Partial) - Nov 2011
Id | Risk Description | Probability |  | Impact (Delays in # of days) | EMV (C*E)
|  | (%) | L/M/H
1 | Delays in completing the Data Model | 0% |  | 0 | 0
2 | Impact is very large because of new data model | 0% |  | 0 | 0
3 | Sharing of tables gets minimized to keep the impact low | 0% |  | 0 | 0
4 | Data migration is not final until end of Nov 11 | 5% | L | 2 | 0.1
5 | Conversion of G1 programs gets delayed | 5% | L | 10 | 0.5
6 | Batch Cycle becomes longer | 30% | L | 15 | 4.5
7 | Project X - taking the resources away from this project | 0% |  | 0 | 0
8 | Project Y Implementation of Base Layer gets delayed | 0% |  | 0 | 0
9 | Datawarehouse can't handle new data by end of Dec 11 | 50% | M | 20 | 10
10 | Other new product - Taking resources away | 30% | L | 10 | 3
11 | Legacy System Changes not completed by end of Dec 11 | 50% | M | 10 | 5
23.1
Note on D4: ANPAC: L - <30% M - >30%, <60% H - >60%

## Data-Dec11
Project A Risk Register (Partial) - Dec 2011
Id | Risk Description | Probability |  | Impact (Delays in # of days) | EMV (C*E)
|  | (%) | L/M/H
1 | Delays in completing the Data Model | 0% |  | 0 | 0
2 | Auto Impact is very large because of new data model | 0% |  | 0 | 0
3 | Sharing of tables gets minimized to keep the auto impact low | 0% |  | 0 | 0
4 | Data migration is not final until end of Nov 11 | 0% | L | 2 | 0
5 | Conversion of G1programs gets delayed | 0% | L | 10 | 0
6 | Batch Cycle becomes longer | 30% | L | 15 | 4.5
7 | Project X - taking the resources away from this project | 0% |  | 0 | 0
8 | Project Y Implementation of Base Layer gets delayed | 0% |  | 0 | 0
9 | Datawarehouse can't handle new data by end of Dec 11 | 50% | M | 20 | 10
10 | Other new product - Taking resources away | 30% | L | 10 | 3
11 | Legacy System Changes not completed by end of Dec 11 | 50% | M | 10 | 5
22.5
Note on D4: ANPAC: L - <30% M - >30%, <60% H - >60%

## Data-Jan12
Project A Risk Register (Partial) - Jan 2012
Id | Risk Description | Probability |  | Impact (Delays in # of days) | EMV (C*E)
|  | (%) | L/M/H
1 | Delays in completing the Data Model | 0% |  | 0 | 0
2 | Auto Impact is very large because of new data model | 0% |  | 0 | 0
3 | Sharing of tables gets minimized to keep the auto impact low | 0% |  | 0 | 0
4 | Data migration is not final until end of Nov 11 | 0% | L | 2 | 0
5 | Conversion of G1programs gets delayed | 0% | L | 10 | 0
6 | Batch Cycle becomes longer | 10% | L | 5 | 0.5
7 | Project X - taking the resources away from this project | 0% |  | 0 | 0
8 | Project Y Implementation of Base Layer gets delayed | 0% |  | 0 | 0
9 | Datawarehouse can't handle new data by end of Jan 12 | 0% | M | 10 | 0
10 | Other new product - Taking resources away | 15% | L | 10 | 1.5
11 | Legacy System Changes not completed by end of Jan 12 | 50% | M | 10 | 5
12 | Issues with coordination just after the code freeze is lifted | 50% | M | 5 | 2.5
13 | Datawarehouse cycle becomes longer | 20% | L | 1 | 0.2
9.5
Note on D4: ANPAC: L - <30% M - >30%, <60% H - >60%

## Data-Feb12
Project A Risk Register (Partial) - Feb 2012
Id | Risk Description | Probability |  | Impact (Delays in # of days) | EMV (C*E)
|  | (%) | L/M/H
1 | Delays in completing the Data Model | 0% |  | 0 | 0
2 | Auto Impact is very large because of new data model | 0% |  | 0 | 0
3 | Sharing of tables gets minimized to keep the auto impact low | 0% |  | 0 | 0
4 | Data migration is not final until end of Nov 11 | 0% | L | 2 | 0
5 | Conversion of G1programs gets delayed | 0% | L | 10 | 0
6 | Batch Cycle becomes longer | 10% | L | 5 | 0.5
7 | Project X - taking the resources away from this project | 0% |  | 0 | 0
8 | Project Y Implementation of Base Layer gets delayed | 0% |  | 0 | 0
9 | Datawarehouse can't handle new data by end of Jan 12 | 0% | M | 10 | 0
10 | Other new product - Taking resources away | 0% | L | 10 | 0
11 | Legacy System Changes not completed by end of Jan 12 | 25% | M | 10 | 2.5
12 | Issues with coordination just after the code freeze is lifted | 0% | M | 5 | 0
13 | Datawarehouse cycle becomes longer | 20% | L | 1 | 0.2
3
Note on D4: ANPAC: L - <30% M - >30%, <60% H - >60%

## EVM Graph
Timescale | EVM (Schedule delay in days) | # of Risks
2011-03-08 | 43 | 8
2011-05-08 | 46.5 | 10
2011-07-08 | 33 | 7
2011-08-08 | 28.1 | 6
2011-09-08 | 25.1 | 6
2011-10-08 | 24.1 | 6
2011-11-08 | 23.1 | 6
2011-12-08 | 22.5 | 4
2012-01-08 | 9.5 | 5
2012-02-08 | 3 | 3