## WBS Hierarchy
Work Breakdown Structure (WBS) Template
Project (Level 0): Website Revamp
Date: February 1, 2020
The purpose of the Work Breakdown Structure (WBS) is to define the full scope of the project in term of deliverables, work packages, and activities.
1. List all deliverables, work packages, and associated activities.
2. List who each activity is assigned to and the estimated start and end dates.
3. Refer to the hierarchy example and other examples if you need clarification.
Deliverable (Level 1) | Work Package ( Level 2) | Activities (Level 3) | Assigned To | Start Date | End Date
1.0. Frontend | 1.1. Landing Page | 1.1.1.Design/Build/Test
| 1.2. Product Page | 1.2.1.Design/Build/Test
| 1.3. Fonts/color schemes | 1.3.1.Design/Build/Test
| 1.4. Customer Support Page | 1.4.1. Design/Build/Test
2.0. Backend | 2.1. Order fulfillment | 2.1.1.
| 2.2. Account creation | 2.2.1.
3.0. eCommerce Integration | 3.1. Install plugins | 3.1.1.
| 3.2. Populate catalog | 3.2.1.
| 3.3. Adjust settings | 3.3.1.
3.3.2.
3.3.3.
| 3.4. | 3.4.1.
3.4.2.
| 3.5. | 3.5.1.
| 3.6. | 3.6.1.
| 3.7. | 3.7.1.
4.0. | 4.1. | 4.1.1.
4.1.2.
4.1.3.
| 4.2. | 4.2.1.
| 4.3. | 4.3.1.
| 4.4. | 4.4.1.
| 4.5. | 4.5.1.
5.0. | 5.1. | 5.1.1.
| 5.2. | 5.2.1.
| 5.3. | 5.3.1.
| 5.4. | 5.4.1.
| 5.5. | 5.5.1.

## WBS Hierarchy Example
0 | Engineering Project
1 | Project Kick Off
2 | Project Planning, Scheduling and Tracking
2.1 |  | Planning & Scheduling
2.2 |  | Tracking Activities & Deliverables
2.3 |  | Weekly Conference Call
2.4 |  | Writing Project Report
3 | Customer Site Visit
3.1 |  | Initial Approval of Drawings
3.1.1 |  |  | Installation Drawings to Sub-contractor
3.2 |  | Site Revisit
4 | Mechanical Engineering
4.1 |  | Mechanical design
4.2 |  | Approval of Drawing
4.3 |  | Release of Pre-Buys
4.3.1 |  |  | Mechanical Pre-Buys
4.3.2 |  |  | Electrical Pre-Buys
4.3.2.1 |  |  |  | Automation Approval
4.4 |  | Detail Drawings
4.4.1 |  |  | Manufacturing Review
4.4.2 |  |  | Review Tolerances
4.5 |  | Engineering Release to Purchasing
4.6 |  | Manufacturing Support - Mechanical
4.7 |  | Redlines/As Builts - Mechanical
5 | Automation Engineering
5.1 |  | Automation Design
5.1.1 |  |  | Programming
5.1.2 |  |  | BOM Release to Purchasing
5.1.3 |  |  | Design Release to Panel Shop
5.2 |  | Approval Drawing
5.3 |  | Develop Sequence of Operations
5.4 |  | Manufacturing Support - Automation
5.5 |  | Redlines/As Builts - Automation
6 | Purchasing
6.1 |  | Pre-Buys
6.2 |  | Mechanical Material Planning
6.2.1 |  |  | Full Mechanical BOM Purchasing
6.2.1.1 |  |  |  | Raw Materials
6.2.1.2 |  |  |  | Components
6.2.1.3 |  |  |  | Outside Services
6.3 |  | Electrical/Pneumatic Material Planning
6.3.1 |  |  | Full Electrical & Pneumatic Purchasing
6.3.1.1 |  |  |  | Raw Materials
6.3.1.2 |  |  |  | Components
6.3.1.3 |  |  |  | Outside Services
6.4 |  | Receiving Inspection
6.5 |  | Vendor Follow Up
7 | Manufacturing
7.1 |  | Manufacturing Hour Breakdown
7.2 |  | Pre-Processing
7.2.1 |  |  | Pre-Process QA Inspection
7.3 |  | Fabrication & Assembly
7.3.1 |  |  | Fabrication QA Inspection
7.3.2 |  |  | Mechanical Assembly QA Inspection
7.4 |  | Grinding
7.4.1 |  |  | Grinding QA Inspection
7.5 |  | Clean Up/Passivation
8 | Electrical Assembly
8.1 |  | Panel Build
8.2 |  | Construction Planning
8.3 |  | Wire/Plumb Machine
8.3.1 |  |  | I/O Checks
9 | Documention
9.1 |  | Accumulate MTRs, Certs, Weld Records
9.2 |  | Write FAT, Sequence of Operations, SAT, IQ/OQ Protocols
9.3 |  | Compile TOP
9.3.1 |  |  | Issue TOP to Customer
10 | Functional Testing
10.1 |  | Verify Fit, Finish, Form and Function
10.1.1 |  |  | Photos
11 | Formal Acceptance Testing
11.1 |  | Confirm FAT Date
11.2 |  | Perform FAT
11.3 |  | Remediation of Issues - Corrective Action
11.4 |  | Customer Sign-Off
12 | Disassembly
12.1 |  | Mechanical Teardown
12.1.1 |  |  | No Part Left Behind
12.2 |  | Electrical Teardown
12.2.1 |  |  | No Part Left Behind
13 | Shipping
13.1 |  | Arrange Transportation
13.2 |  | Design/Build crates
13.3 |  | Packaging
13.4 |  | Load Truck
14 | On Site Services
14.1 |  | Pre-Planning
14.2 |  | Coordinate with Installation Contractor or Custoomer
14.3 |  | Installation supervision
14.4 |  | SAT Execution
14.5 |  | Customer Training
14.6 |  | IQ/OQ Execution

## WBS Bicycle Diagram
Example: WBS Diagram
The Work Breakdown Structure identifies the project’s tasks and provides a framework for organizing and managing the work. Two methods for presenting a work breakdown structure (WBS) are the WBS outline and the WBS diagram.
Bicycle
Frame set
Derailers
Frame Tubes
Fork
Wheels
Integration
Brakes
Shifting System
Project Management
Frame Stays
Bottom Bracket Shell
Front Derailer
Rear Derailer
Hub
Spokes
Rim
Saddle
Build
Handlebar
Prototype
Test

## WBS Diagram
Example: WBS Diagram
Project Meyer
Initiate Project
Develop Project Charter
Plan Project
Develop Work Plan
Develop Project Control Plan
Finalize Project Plan and Gain Approvals
Develop Work Breakdown Structure
Develop Project Staffing Plan
Develop
Project Schedule
Develop
Project
Budget
Develop Quality Management Plan
Define Scope
Define Requirements
Define High-Level Roles
Define High-Level Budget
Identify High-Level Control
Strategies
Finalize Charter
Develop Communication Plan
The Work Breakdown Structure identifies the project’s tasks and provides a framework for organizing and managing the work. Two methods for presenting a work breakdown structure (WBS) are the WBS outline and the WBS diagram.
Execute and Control Project
Design Content formats
Build the Framework
Test the Framework
Implement the Framework
Close the Project
Design the Framework
Define stages and activities
Design
web Delivery Tool
Write the content
Review content for quality
Build web tool prototype
Test web tool usability
Test content usability
Adjust tool and content based on feedback
Move web tool to production environment
Announce
Tool
availability
Conduct post project review
Celebrate
Monitor and Control Project
Stakeholder Identification

## WBS Outline PM
Level | Project | Deliverables | Assigned To | Start Date | Low Hours | High Hours | Likely Hours | PERT Hours | PERT Days | End Date | Cost ($) @ 10/hr | Duration (Days) | Duration (Weeks)
1 | Initiation
2 | Develop Project Charter | Project Charter
2 | Identify Stakeholders | Stakeholder Register
1 | Planning
2 | Develop Project Management Plan | Project Management Plan
2 | Collect Requirements | Requirements Document
3 | Requirements documents
3 | Requirements Management Plan
3 | Requirements Traceability Matrix
2 | Define Scope | Project Scope statement
2 | Create WBS | WBS
3 | WBS
3 | WBS Dictionary
3 | Scope Baseline
3 | Project Document Updates
2 | Define Activities | Milestone Chart
3 | Activity list
3 | Activity attributes
3 | Milestone list
2 | Sequence Activities | Project Schedule Network Diagrams
2 | Estimate Activity Resources | Resource Breakdwon Structure
3 | Activity resource requirements
3 | Resource breakdown structure
3 | Project document updates
2 | Estimate Activity Durations | Activity Duration Estimates
3 | Activity duration estimates
3 | Project document updates
2 | Develop Schedule | Project Schedule
3 | Project Schedule
3 | Schedule Baseline
3 | Schedule data
3 | Project document updates
2 | Estimate Costs | Cost Estimates Report
3 | Activity cost estimates
3 | Basis of estimates
3 | Project document updates
2 | Determine Budget | Budget Report
3 | Cost performance baseline
3 | Project funding requirements
3 | Project document updates
2 | Plan Quality | Quality Plan
3 | Quality management plan
3 | Quality metrics
3 | Quality checklists
3 | Process improvement plan
2 | Develop Human Resource Plan | Human Resource Plan
2 | Plan Communication | Communication Plan
2 | Plan Risk Management | Risk Management plan
2 | Identify Risks | Risk Register
2 | Perform Risk Reister Quantitative & Qualitative Analysis | Risk Register Updtates
2 | Plan Risk Responses | Risk Register Updtates
2 | Plan Pocurements | Procurement Management Plan
3 | Procurement management plan
3 | Procurement statement of work
3 | Make-or-buy decisions
3 | Procurement documents
3 | Source selection criteria
3 | Change requests
1 | Execution Process
2 | Direct & Manage Project Execution | Work performance information
3 | Work performance information
3 | Change requests
3 | Project management plan updates
3 | Project document updates
2 | Perform quality Assurance | Quality Docuements
3 | Organizational process asset updates
3 | Change requests
3 | Project management plan updates
3 | Project document updates
2 | Acquire ,Develop, Manage Project Team | Staff Assignment documents
3 | Project staff assignments
3 | Resource calendars
3 | Project management plan updates
3 | Team performance assessment
3 | Enterprise environmental factor Updates
3 | Organizational process assets updates
3 | Project management plan updates
3 | Change requests
2 | Stakeholder Management | Chane Requests
3 | Change requests
3 | Project management plan updates
3 | Project document updates
1 | Monitoring & Controlling
2 | Monitor and control Project work | Chane Requests
3 | Change requests
3 | Project management plan updates
3 | Project document updates
2 | Perform Integrated Change Control | Chane Requests Status Updates
3 | Change request status updates
3 | Project management plan updates
3 | Project document updates
2 | Verify Scope | Accepted Deliverables
3 | Accepted deliverables
3 | Change requests
3 | Project document updates
2 | Control Scope | Work performance information
3 | Work performance measurements
3 | Organizational process assets updates
3 | Change requests
3 | Project management plan updates
3 | Project document updates
2 | Control schedule | Work performance information
3 | Work performance measurements
3 | Organizational process assets updates
3 | Change requests
3 | Project management plan updates
3 | Project document updates
2 | Control cost | Work performance information
3 | Work performance measurements
3 | Budget forecasts
3 | Organizational process assets updates
3 | Change requests
3 | Project management plan updates
3 | Project document updates
2 | Perform quality control | Quality Control Documents
3 | Quality control measurements
3 | Validated deliverables
3 | Organizational process assets updates
3 | Change requests
3 | Project management plan updates
3 | Project document updates
2 | Report performance | Performance Reports
3 | Performance reports
3 | Organizational process assets updates
3 | Change requests
2 | Monitor and control risks | Risk Register Updates
3 | Risk register updates
3 | Organizational process assets updates
3 | Change requests
3 | Project management plan updates
3 | Project document updates
2 | Administer procurements | Procurement Documents
3 | Procurement documentation
3 | Organizational process assets
3 | updates
3 | Change requests
3 | Project management plan updates
1 | Closing
2 | Conduct post project review | Final product or service
3 | Final product, service, or result transition
3 | Organizational process assets Updates
2 | Close Procurements | closed procurements
3 | Closed procurements
3 | Organizational process assets updates
Note on C85: STANFORDR: If you require NLDC accounts open in your schedule, please consult Measurements Administrator

## WBS Outline Example
Level | Project Name | Deliverables | Assigned To | Start Date | Low Hours | Likely Hours | High Hours | PERT Hours | PERT Days | End Date | Cost ($) @ 10/hr | Duration (Days) | Duration (Weeks)
0 | Project Meyer | University Website | Rama | [7 empty] | 5148.3333 |  | 12.0083
1 | Initiation | Project charter, Stakeholder Register | Jennifer | [7 empty] | 806.6667 |  | 1.1542
2 | Develop Project Charter | Project Charter | Jennifer | 2013-02-03 | [5 empty] | 2013-02-08 | 345 | 0 | 0
3 | Define Scope |  | Jennifer | 2013-02-04 | 3 | 5 | 7 | 5 | 0.625 | 2013-02-04 | 50 | 0.625 | 0.125
3 | Define Requirements |  | Jennifer | 2013-02-05 | 7 | 12 | 25 | 13.3333 | 1.6667 | 2013-02-06 | 133.3333 | 1.6667 | 0.33333
3 | Define High Level Requirments |  | Jennifer | 2013-02-06 | 5 | 7 | 9 | 7 | 0.875 | 2013-02-06 | 70 | 0.875 | 0.175
3 | Define High Level Budget |  | Jennifer | 2013-02-07 | 4 | 6 | 7 | 5.8333 | 0.72917 | 2013-02-07 | 58.3333 | 0.72917 | 0.14583
3 | Finalize Charter |  | Jennifer | 2013-02-08 | 2 | 3 | 6 | 3.3333 | 0.41667 | 2013-02-08 | 33.3333 | 0.41667 | 0.083333
2 | Identify Stakeholders | Stakeholder Register | Walton | 2013-02-04 | 8 | 10 | 22 | 11.6667 | 1.4583 | 2013-02-05 | 116.6667 | 1.4583 | 0.29167
1 | Planning | Work Plan, WBS, Staffing Plan, Project Schedule, Budget Report, Communication Plan, Risk Management Plan, Risk Register, Risk Register Updates | Rama | [7 empty] | 1178.3333 |  | 2.9458
2 | Develop Work Plan | Work Plan | Chris | 2013-05-15 | [5 empty] | 2013-04-30 | 740 |  | 1.85
3 | Develop Work Breakdown Structure | WBS | Aaron | 2013-06-14 | 20 | 25 | 35 | 25.8333 | 3.2292 | 2013-06-19 | 258.3333 | 3.2292 | 0.64583
3 | Develop Project Staffing Plan | Staff Plan | Chris | 2013-05-17 | 12 | 14 | 28 | 16 | 2 | 2013-05-21 | 160 | 2 | 0.4
3 | Develop Project Schedule | Project Schedule | Megan | 2013-07-18 | 9 | 16 | 24 | 16.1667 | 2.0208 | 2013-07-22 | 161.6667 | 2.0208 | 0.40417
3 | Develop Project Budget | Budget Report | Jennifer | 2013-04-26 | 12 | 14 | 28 | 16 | 2 | 2013-04-30 | 160 | 2 | 0.4
2 | Develop Project Control Plan | Communication Plan | Chris | 2013-05-20 | [5 empty] | 2013-05-20 | 278.3333 |  | 0.69583
3 | Develop Communication Plan | Risk Management plan | Megan | 2013-05-16 | 6 | 24 | 13 | 19.1667 | 2.3958 | 2013-05-20 | 191.6667 | 2.3958 | 0.47917
3 | Develop Quality Management Plan | Risk Register | Megan | 2013-05-17 | 4 | 10 | 8 | 8.6667 | 1.0833 | 2013-05-20 | 86.6667 | 1.0833 | 0.21667
2 | Finalize Project Plan and Gain Approvals | Risk Register Updtates | Chris | 2013-05-18 | 12 | 14 | 28 | 16 | 2 | 2013-05-21 | 160 | 2 | 0.4
1 | Execution Process | Framework Content, Tool, Quality, Prototype | Chris | [7 empty] | 521.6667 |  | 1.3042
2 | Design Framework | Framework Design documents | Megan | 2013-05-18 | [5 empty] | 2013-05-21 | 261.6667 |  | 0.65417
3 | Define framework stages and activities | Framework activities documents | Megan | 2013-05-18 | 4 | 10 | 8 | 8.6667 | 1.0833 | 2013-05-20 | 86.6667 | 1.0833 | 0.21667
3 | Design framework content formats | Content format documents | Megan | 2013-05-19 | 4 | 10 | 9 | 8.8333 | 1.1042 | 2013-05-20 | 88.3333 | 1.1042 | 0.22083
3 | Design web framework delivery tool | Tool | Megan | 2013-05-20 | 4 | 10 | 8 | 8.6667 | 1.0833 | 2013-05-21 | 86.6667 | 1.0833 | 0.21667
2 | Build the Framework | Framework | Megan | 2013-05-21 | [5 empty] | 2013-05-27 | 260 |  | 0.65
3 | Write the framework content | Framework content documents | Megan | 2013-05-22 | 4 | 10 | 8 | 8.6667 | 1.0833 | 2013-05-23 | 86.6667 | 1.0833 | 0.21667
3 | Review framework content for quality | Quality documents | Megan | 2013-05-23 | 4 | 10 | 8 | 8.6667 | 1.0833 | 2013-05-24 | 86.6667 | 1.0833 | 0.21667
3 | Build web tool prototype | Prototype | Megan | 2013-05-24 | 4 | 10 | 8 | 8.6667 | 1.0833 | 2013-05-27 | 86.6667 | 1.0833 | 0.21667
1 | Monitoring & Controlling | Test Report, Usability Report, Feedback, Availability Report, Go live Report, Framework Implementation Report | June | [7 empty] | 2336.6667 |  | 5.8417
2 | Test the Framework | Framework test report | Chris | 2013-04-26 | [5 empty] | 2013-05-06 | 745 |  | 1.8625
3 | Test usability of web tool | Usability report | Jennifer | 2013-04-26 | 12 | 28 | 18 | 23.6667 | 2.9583 | 2013-04-30 | 236.6667 | 2.9583 | 0.59167
3 | Test usability of content | Content Verification report | Chris | 2013-04-02 | 12 | 28 | 34 | 26.3333 | 3.2917 | 2013-04-05 | 263.3333 | 3.2917 | 0.65833
3 | Adjust framework based on user feedback | Feedback report | Jennifer | 2013-04-26 | 12 | 28 | 23 | 24.5 | 3.0625 | 2013-05-06 | 245 | 3.0625 | 0.6125
2 | Implement Framework | Framework implementation report | Chris | 2013-01-21 | [5 empty] | 2011-12-30 | 423.3333 |  | 1.0583
3 | Move framework to production environment | Go live Report | Jennifer | 2013-01-21 | 12 | 28 | 12 | 22.6667 | 2.8333 | 2013-01-23 | 226.6667 | 2.8333 | 0.56667
3 | Announce availability of framework | Availability Report | Chris | 2011-12-28 | 12 | 23 | 14 | 19.6667 | 2.4583 | 2011-12-30 | 196.6667 | 2.4583 | 0.49167
1 | Closing | Final Product , Closed Procurements document | Chris | [7 empty] | 305 |  | 0.7625
2 | Conduct post project review | Final product or service | Chris | 2011-12-28 | 14 | 22 | 18 | 20 | 2.5 | 2011-12-30 | 200 | 2.5 | 0.5
3 | Final product, service, or result transition
3 | Organizational process assets Updates
2 | Close Procurements | closed procurements | Chris | 2011-12-31 | 7 | 12 | 8 | 10.5 | 1.3125 | 2012-01-02 | 105 | 1.3125 | 0.2625
3 | Closed procurements
3 | Organizational process assets updates
Formulas:
End Date = WORKDAY([Start Date],[PERT Days])
Start Date = [Start Date, row below]
Note on N1: Phillip George: Divides Column M result by 5.